## Goods
Country: Nigeria
Program: ACE SPED
Date: January 07, 2023
Applicable Period: January - December 2023
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN
|  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[5 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
List of Contracts
Procurement of Project Vehicles | UNN/ACESPED/GDS//05/2023 | 4 | 250000 | Selective Tendering | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | N/A | 07/03/2023 | 27/03/2023 | 07/04/2023 | N/A | Plan | 250000 | 17/04/2023 | N/A | 28/04/2023 | N/A | 26/05/2023 | 26/05/2023
[7 empty] | Actual | [7 empty] | Actual
Equipment for electric power systems laboratory | UNN/ACESPED/GDS//05/2023 | 9 | 600000 | NCB | Post | Post Review | Plan | 17/02/2023 | 24/02/2023 | 06/03/2023 | 06/03/2023 | 06/04/2023 | 20/04/2023 | N/A | Plan | 600000 | 01/05/2023 | 15/05/2023 | 15/05/2023 | N/A | 16/06/2023 | 16/06/2023
[7 empty] | Actual | [7 empty] | Actual
[7 empty] | Actual | [7 empty] | Actual
Total Cost |  |  | 850000 | [12 empty] | 850000
Fill gray cells only!

## Works
Country: Nigeria
Program: Africa Centre of Excellence for Sustainable Power and Energy Development (ACE-SPED)
Date: January 07, 2023
Applicable Period: January - December 2023
Project ID:
Implementing Agency: University of Nigeria, Nsukka | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  | Basic Data | [8 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
Description* | Package Number | Lot Number | Lumpsum or Bill of Quantities | Procurement Method | Estimated Amount in US $ | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
Norm Duration of Proc Steps | [5 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Plan |  | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
Renovation of international scholars hostels with appropriate furnishings, fittings and back-up power | UNN/ACESPED/WRK//01/2023 | 1 | BOQ | National Shopping | 70000 | Post Qualification | Post Review | Plan | 17/03/2023 | N/A | N/A | 24/03/2023 | 07/04/2023 | 21/04/2023 | N/A | Plan | 70000 | 28/04/2023 | N/A | 12/05/2023 | 19/05/2023 | 19/07/2023 | 19/12/2023 | 70000
[8 empty] | Actual | [7 empty] | Actual
Total Cost |  |  |  |  | 70000 | [11 empty] | 70000
Fill gray cells only!
NB: Submission of BER under NCB implies submission by the Evaluation Committee to Management for Approval, and not to the Bank