## Sheet1
Name of Center: ACESPED
Institution: University of Nigeria, Nsukka |  |  |  | On Schedule
Country: Nigeria
Center Leader: Engr. Prof. Emenike C. Ejiogu |  |  |  | Behind Schedule
Annual Workplan (January 1-Decemebr 31, 2021)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated DLI Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 1 Basic and Full Readiness
Activity 1: Development of ACE-SPED website | To develop a customized web-site for easy access and dissemination of Centre activities | [13 empty] | ACE-SPED website operationalized |  | 10000 | 10000 | 0 | Inf. Officer
Activity 2: Development and production of M.Eng/MSc and PhD curricula and students’ handbook | To develop Curricula for the M.EngMsc and PhD programs of the ACE-SPED | [13 empty] | M.Eng/MSc, PhD curricula and students’ handbook developed and produced. |  | 10000 | 10000 | 0 | CL/APC
Activity 3: Production and signing of MoUs/Launch of Center | To establish strong partnership with Institutions and smooth take off of the center. | [13 empty] | A robust and benefit-oriented MoUs with partners signed and center launched. |  | 50000 | 50000 | 0 | CL
Action 2: DLI 2; Development of Impact of ACESPED
Activity 1: Securing University Senate recognition of ACE-SPED as a statutory University unit | For recognition of ACE-SPED as a statutory unit for budgetary purposes | [13 empty] | Recognition, visibility, ownership and sustainability achieved |  | 1000 | 1000 | 0 | CL
Activity 2: Attendance to ACE-related meetings and events outside the University | To attend ACE related meetings outside the University. | [13 empty] | Information exchange and reports on project development objectives accomplished. |  | 72000 | 62000 | 10000 | CL
Action 3: DLI 3; Quantity of Students
Activity 1: Advertisement, recruitment drive for intake of students | Adverts are made for the intake of students for the M.Eng and Ph.D programs. | [13 empty] | Adverts for intake of students are made. |  | 2000 | 2000 | 0 | CL/APC
Activity 2: Selection and admission of M.Eng/MSc and PhD candidates. | Candidates who applied to the various programs of the ACE-SPED are screened for admission. | [13 empty] | Qualified students are admitted based on merit. |  | 2000 | 2000 | 0 | CL/APC
Action 4: DLI 4: Quality of Education and Research
Sub-activity 1: Education
Activity 1: Vocational outreach educational programs for secondary school students | To undertake vocational outreach educational program to select secondary and primaries schools | [13 empty] | Vocational outreach educational program conducted. |  | 1500 | 1250 | 250 | APC
Activity 2: Outreach educational program for females and underserved communities | To conduct outreach educational programs for females and underserved communities | [13 empty] | Outreach programs are conducted |  | 2500 | 1750 | 750 | APC
Activity 3: On-site workshops and short trainings at ACE-SPED partner sites | To conduct on-site workshops and trainings at partner sites. | [13 empty] | Workshops and short training conduct at partner sites |  | 10400 | 400 | 10000 | APC/ILO
Activity 4: Staff exchange for sabbatical and visiting lectureship | To draw highly qualified manpower to teach and supervise students at the ACE-SPED | [13 empty] | Highly skilled and competent manpower attracted to the ACE-SPED |  | 25000 | 12500 | 12500 | CL/ILO
Activity 5: Training of Faculty on the use of multimedia teaching aids | To train faculty on use of multimedia teaching aids | [13 empty] | Faculty are trained to use multimedia teaching aids |  | 17000 | 12000 | 5000 | CL/APC
Activity 6: Faculty and students’ support | To support faculty and students through conference/workshop/seminar attendance, research publications, internet access, scholarly visits and development of lecture materials, patents, etc. | [13 empty] | Support provided to staff and students. |  | 112500 | 87500 | 25000 | CL
Activity 7: Provision of Scholarships for MEng/MSc and PhD students including research costs to regional students. | To provide fellowship, on competitive basis, to regional students to cover cost of studies and research | [13 empty] | Regional students enrolled in the ACE are supported. |  | 70000 | 70000 | 0 | CL/APC
Activity 8: Organization of short courses and workshops to address specific skill needs for industry | To organize periodic short courses to address skill gaps in industry | [13 empty] | Short courses conducted and qualified experts produced |  | 75000 | 62500 | 12500 | CL/APC
Activity 9: Language course for non-English speaking students | To provide English language training for non-English speaking students | [13 empty] | Non-English speaking student are taught English |  | 2500 | 2500 | 0 | DCL/APC
Activity 10: Development of educational materials for outreach programs. | To develop and produce educational materials for outreach programs. | [13 empty] | Educational materials for the vocational outreach program developed |  | 3800 | 3560 | 240 | CL/APC
Activity 11: Regional workshops | To organize periodic regional workshops to promote inclusiveness in ACE-SPED academic and research programmes | [13 empty] | Regional workshops organised |  | 10000 | 8000 | 2000 | CL
Sub-Activity 2: Research
Activity 1: Subscription to relevant international journals and databases. (Research4Life) | To subscribe to relevant international journals and academic databases | [13 empty] | Subscriptions are made to relevant international journals and academic databases |  | 5000 | 3750 | 1250 | ARC/APC
Activity 2: Gap analysis survey to ascertain the research needs of the sector | To undertake gap analysis survey with a view to ascertaining the research needs of the sector | [13 empty] | Existing gap in the sector is documented |  | 20000 | 10000 | 10000 | CL/ILO
Activity 3: Fabrication of relevant state-of-the-art R & D equipment | To fabricate relevant R & D equipment | [13 empty] | Relevant Research fabricated and operationalized |  | 18750 | 6250 | 12500 | CL
Activity 4: Capacity building of core team of Research Leads to head the thematic areas | To strengthen the research capabilities of core Research Leads in the area of modern approaches to research to enhance productivity | [13 empty] | Core team research leads developed for improved research delivery |  | 70000 | 60000 | 10000 | CL/ARC
Activity 5: Training of faculty and technical staff on use of state-of-the-art equipment | To improve the staff proficiency in the use of state-of-the art equipment | [13 empty] | Training of faculty & technical staff for optimal utilization of state-of-the-art equipment completed |  | 10000 | 7500 | 2500 | DCL
Activity 6: Development and review of research proposals in the thematic areas | To develop and review research proposals in the thematic areas in collaboration with the sector partners | [13 empty] | Research proposals reviewed and gaps addressed |  | 600 | 400 | 200 | ARC
Activity 7: Training of safety and security personnel | To train safety and security personnel on the latest measures and counter treats strategies to life and property | [13 empty] | Safety and security are assured |  | 3750 | 2500 | 1250 | ESSO
Activity 8: Organisationof seminars/workshops and publication in journals | To document, disseminate, prototype and in extension patent research results | [13 empty] | Research results are documented |  | 2600 | 2000 | 600 | DCL
Activity 9: Field trips | To expose students and staff to industry sector activities, on-site and data collection | [13 empty] | Field tripS executed |  | 5000 | 3750 | 1250 | ILO/ARC
Activity 10: Field trials | To ascertain the workability and performance of developed prototypes | [13 empty] | Field trials executed |  | 7500 | 2500 | 5000 | ILO/ARC
Activity 11: Software purchase and development | To purchase and develop relevant software required for energy and power research | [13 empty] | Software is developed or procured |  | 9000 | 7000 | 2000 | ARC/APC
Activity 12: Facilitate exchange and sharing of information and library resources between ACE-SPED and partners | To facilitate exchange of information and resources between ACE-SPED staff and partners | [13 empty] | Information and library resources shared |  | 900 | 200 | 700 | ILO
Activity 13: Pursuit of International accreditation of M.Eng and Ph.D programs | To pursue International accreditation of M.Eng and Ph.D programs of the ACE-SPED | [13 empty] | Internationally accredited Programs by HCRES |  | 225000 | 225000 | 0 | CL
Activity 14: Undertake industrial liaison visits | To promote effective engagement between ACESPED and partners | [13 empty] | Industrial Liaison visits undertaken |  | 6000 | 2000 | 4000 | ARC/ILO
Sub-Activity 3: Infrastructure
Activity 1: Upgrading of Laboratory of Industrial Electronics, Power Devices and New Energy Systems | To furnish and equip the Industrial Electronics/New Energy Laboratory for practice orientation in energy and power research | [13 empty] | Well-equipped and functional Industrial Electronics/New Energy Laboratory |  | 125000 | 100000 | 25000 | CL
Activity 2: Provision of Equipment for ACESPED Fabrication Workshop | To furnish and equip the Fabrication Workshop | [13 empty] | Well-equipped Fabrication Workshop |  | 135000 | 125000 | 10000 | CL
Activity 3: Provision of Equipment for Renewable Energy Laboratory | To furnish and equip the Renewable Energy Laboratory | [13 empty] | Well-equipped Renewable Energy Lab. |  | 105000 | 95000 | 10000 | CL
Activity 4: Provision of Equipment forAdvanced Materials Characterization Laboratory | To furnish and equip the Advanced Materials Lab | [13 empty] | Well-equipped Energy Materials Laboratory |  | 180000 | 170000 | 10000 | CL
Activity 5: Provision of Equipment for Electric Power Systems Laboratory | To furnish and equip Electric Power Systems Lab | [13 empty] | Well-equipped Electric Power Systems Laboratory |  | 331000 | 325000 | 6000 | CL
Activity 6: Procurement of Project Vehicles | To acquire vehicles that would enhance mobility in the Centre | [13 empty] | 2 No project vehicles procured |  | 160000 | 160000 | 0 | CL
Activity 7: Renovation of international scholars’ hostels with appropriate furnishings, fittings and back-up power | To provide a conducive living environment for international students | [13 empty] | International scholars’ hostels renovated and furnished with back-up power supply. |  | 75000 | 5000 | 70000 | CL
Activity 8: Preparation of Building Plan, award of contract and construction of ACE-SPED Service Core building complex | Preparation of Building Plans and Award of Contract and Commencement of Construction of ACE-SPED Service Core building complex | [13 empty] | Land mark ACE-SPED service core building complex constructed and operationalized. |  | 1420000 | 1420000 | 0 | CL
Activity 9: Upgrading of facilities in the Seminar Room for visual learning, incl. video conferencing and webinars. | To provide visual learning facilities in the Seminar Room. | [13 empty] | Facilities for virtual learning provided. |  | 100000 | 100000 | 0 | CL
Activity 10: Renovation and upgrading of 5 no. classrooms, including the provision of teaching aids and back-up power solutions. | To renovate and upgrade 5 no classrooms with modern teaching aids (multimedia facilities, white boards, overhead projectors) and back-up power solutions. | [13 empty] | Five (5) classrooms upgraded and renovated |  | 120000 | 120000 | 0 | CL
Action 5: DLI 5; Relevance of Education and Research
Activity 1: Workshop with ACE-SPED partners on curricula | To review the developed curricula and receive inputs from stakeholders | [13 empty] | Reviewed and acceptable curricula |  | 40000 | 20000 | 20000 | CL
Activity 2: Securing approval of the M.Eng/MSc and Ph.D programs at the Postgraduate School and the University Senate. | To pursue the approval of the developed curricula for M.Eng/Msc and Ph.D at the Postgraduate school and the University Senate. | [13 empty] | Approved programs |  | 2000 | 2000 | 0 | CL
Activity 3: Publication of ACE-SPED Journal, Bulletin and Newsletter. | Formation of the editorial board, production studio, material acquisition, production of the journal, bulletin, newsletter and promotion of the publication, feedback | [13 empty] | ACE-SPED journal, Bulletin and Newsletter |  | 4000 | 4000 | 0 | ARC
Action 6: DLI 6; Timeliness of Fiduciary Management
Activity 1: Development of Implementation work plan | To produce a focused overall work plan to assist in accountability & smooth operations of project. | [13 empty] | A detailed and focused work plan developed and produced |  | 25000 | 20000 | 5000 | CL
Activity 2: Pre-bid Conference | To sensitize the potential bidders on WB procurement procedures & guidelines | [13 empty] | Enhanced competitiveness of the bidding process achieved |  | 10000 | 8000 | 2000 | CL/PMO/PO
Activity 3: Annual procurement, financial and external audit reports | To prepare annual procurement, financial and external audit reports | [13 empty] | Annual procurement, financial & audit reports produced |  | 6000 | 6000 | 0 | CL
Activity 4: Organize regular planning meetings s with ACE-SPED partners and major stake holders | To organize consultative forums involving all major stake holders in preparation for project take-off. | [13 empty] | Meeting held and detailed project documents produced |  | 4200 | 4000 | 200 | DCL/ILO
Activity 5: Scheduled ACE meetings (Int’l Advisory Board, Industrial Advisory Board, Management Committee Research and Academic Co-ordination) | Scheduled ACE meetings (Int’l Advisory Board, Industrial/Sectoral Advisory Board, Management Committee Research and Academic Co-ordination) | [13 empty] | Meetings held with documentary of proceedings. |  | 20000 | 16000 | 4000 | CL
Action 7: DLI 7; Institutional Impact
Activity 1: Upgrading of UNN internet network (Lionet) for ACE-SPED facilities | To provide unrestricted internet access for ACE-SPED facilities | [13 empty] | LIONET Internet network is upgraded. |  | 150000 | 150000 | 0 | CL